## MD Table
¦ |  | ¦ | Priority | ¦ | Status (★) | ¦ | ETD | ¦ | Notes | ¦ |  | Priority | Status (★) | Implementation Date
¦--- |  | ¦--- |  | ¦--- |  | ¦--- |  | ¦--- |  | ¦ | PouchDB
¦ | PouchDB | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | login | 2 | ★★☆☆☆ | 2017-01-05
¦ | login | ¦ | 2 | ¦ | ★★☆☆☆ | ¦ | 2017-01-05 | ¦ |  | ¦ | reports | 2.1 | ☆☆☆☆☆ | 2017-01-05
¦ | reports | ¦ | 2.1 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-05 | ¦ |  | ¦ | scheduling | 2.2 | ☆☆☆☆☆ | 2017-01-05
¦ | scheduling | ¦ | 2.2 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-05 | ¦ |  | ¦ | Shifts | 2.3 | ☆☆☆☆☆ | 2017-01-06 | UI-ionic2
¦ | Shifts | ¦ | 2.3 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-06 | ¦ |  | ¦ | Custom Code
¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
¦ | Custom Code | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | Date Parsing | 1 | ☆☆☆☆☆ | 2017-01-05
¦ | Date Parsing | ¦ | 1 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-05 | ¦ |  | ¦ | Angular 2 Forms
¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
¦ | Angular 2 Forms | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | Report | 3 | ☆☆☆☆☆ | 2017-01-07
¦ | Report | ¦ | 3 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-07 | ¦ |  | ¦ | Login | 3.1 | ☆☆☆☆☆ | 2017-01-07
¦ | Login | ¦ | 3.1 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-07 | ¦ |  | ¦ | Settings | 3.2 | ☆☆☆☆☆ | 2017-01-07
¦ | Settings | ¦ | 3.2 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-07 | ¦ |  | ¦ | Shifts | 3.3 | ☆☆☆☆☆ | 2017-01-07
¦ | Shifts | ¦ | 3.3 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-07 | ¦ |  | ¦ | UI-ionic2
¦ | UI-ionic2 | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | Home Page | 4 | ★★★☆☆ | 2017-01-08
¦ | Home Page | ¦ | 4 | ¦ | ★★★☆☆ | ¦ | 2017-01-08 | ¦ |  | ¦ | Build
¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
¦ | Build | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | Android | 4 | ☆☆☆☆☆ | 2017-01-09
¦ | Android | ¦ | 4 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-09 | ¦ |  | ¦ | iOS | 4 | ☆☆☆☆☆ | 2017-01-10
¦ | iOS | ¦ | 4 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-10 | ¦ |  | ¦ | Windows | 4 | ☆☆☆☆☆ | 2017-01-11
¦ | Windows | ¦ | 4 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-11 | ¦ |  | ¦ | Browser | 4 | ☆☆☆☆☆ | 2017-01-12
¦ | Browser | ¦ | 4 | ¦ | ☆☆☆☆☆ | ¦ | 2017-01-12 | ¦ |  | ¦
¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | @next
¦ | @next | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | GeoLocation
¦ | GeoLocation | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | Reports |  | ☆☆☆☆☆ | TBD
¦ | Reports | ¦ |  | ¦ | ☆☆☆☆☆ | ¦ | TBD | ¦ |  | ¦ | App |  | ☆☆☆☆☆ | TBD
¦ | App | ¦ |  | ¦ | ☆☆☆☆☆ | ¦ | TBD | ¦ |  | ¦ | GeoFence |  | ☆☆☆☆☆ | TBD
¦ | GeoFence | ¦ |  | ¦ | ☆☆☆☆☆ | ¦ | TBD | ¦ |  | ¦ | Report
¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
¦ | Report | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | HB Wreport |  | ☆☆☆☆☆ | TBD
¦ | HB Wreport | ¦ |  | ¦ | ☆☆☆☆☆ | ¦ | TBD | ¦ |  | ¦

## Table
| Priority | Status (★) | Implementation Date | Completed |  | MISC Items
PouchDB |  |  |  |  | Date MetaData: | Need to encode a creation date into reports which is not influenced by user and read-only (probably not possible… but whatever I can do there
login | 2 | ★★☆☆☆ | 2017-01-05
reports | 2.1 | ★★☆☆☆ | 2017-01-05
scheduling | 2.2 | ★★☆☆☆ | 2017-01-05
Shifts | 2.3 | ★★☆☆☆ | 2017-01-06
Custom Code
Date Parsing | 1 | ★★★★★ | 2017-01-05 | 2017-01-09
Angular 2 Forms
Report | 3 | ★★☆☆☆ | 2017-01-07
Login | 3.1 | ★★☆☆☆ | 2017-01-07
Settings | 3.2 | ☆☆☆☆☆ | 2017-01-07
Shifts | 3.3 | ☆☆☆☆☆ | 2017-01-07
UI-ionic2
Home Page | 4 | ★★★☆☆ | 2017-01-08
Build
Android | 4 | ☆☆☆☆☆ | 2017-01-09
iOS | 4 | ☆☆☆☆☆ | 2017-01-10
Windows | 4 | ☆☆☆☆☆ | 2017-01-11
Browser | 4 | ☆☆☆☆☆ | 2017-01-12
@next
GeoLocation
Reports |  | ☆☆☆☆☆ | TBD
App |  | ☆☆☆☆☆ | TBD
GeoFence |  | ☆☆☆☆☆ | TBD
Report
HB Wreport |  | ★★★★☆ | TBD

## ToDo Qs
Questions which are still unclear:
Load user data on app load (globally available object on load)
Login stuff:
Check if user has already logged in (first load query)
Validate user with CouchDB
Store user data on device (reliable/simple)
retrieve user data from local storage